## Where we are
Hermes: where we are
Last updated | Oct 17 2:25 AM ET
Status | Count
Done
In progress
Blocked
On hold
Not started
Total
% done
Next up (Blocked and Not started, top of list)
Open the Tasks tab and filter Status. Blocked items name exactly what is missing.

## Archive
ID | Project | Task | Status | Next step | Blocked by / waiting on | Owner | Updated | Archived

## Tasks
ID | Project | Task | Status | Next step | Blocked by / waiting on | Owner | Updated
H1 | Setup | Hermes Agent installed on the new laptop (i5-7300U, 16 GB, Windows 10 Pro 22H2) | Done | Verify in H2 | Per Neko Oct 17. Not yet seen by Claude (this chat is linked to the old i3 laptop) | Neko | Oct 17 2:25 AM ET
H2 | Setup | Verify the install: run hermes doctor, then hermes, ask it one small question | Not started | Mon Oct 19, 9-10 AM ET session | Neko at the new laptop | Claude | Oct 17 2:25 AM ET
H3 | Setup | Model: DeepSeek chosen per Neko. Confirm the exact model supports tool calling and 64K+ context, check the monthly cost, and set a spend limit | In progress | Check the model in Hermes config with Neko; any spend needs his yes | Neko: yes on spend. Key goes only in Hermes config, never in chat | Claude | Oct 17 2:25 AM ET
H4 | Setup | Fallback model so one rate limit does not stall a run (OpenRouter free or NVIDIA NIM free credits) | Not started | Add fallback_providers to Hermes config after H3 | H3 | Claude | Oct 17 2:25 AM ET
H5 | Setup | Keep the laptop awake: Screen and Sleep set to Never, lid close set to Do nothing, plugged in | Not started | Neko does it at the laptop (steps were given Oct 15) | Neko at the new laptop | Neko | Oct 17 2:25 AM ET
H6 | Safety | Install Docker Desktop (WSL2) and set Hermes terminal backend to Docker so its commands run in a sandbox | Not started | Install after H2 passes | H2 | Claude | Oct 17 2:25 AM ET
H7 | Safety | Dedicated-machine rules: no personal logins in any browser Hermes can reach; API server bound to 127.0.0.1 with a long random key; secrets only in Hermes config | Not started | Set during the Monday session | H2 | Claude | Oct 17 2:25 AM ET
H8 | Reach | Telegram gateway so Hermes messages Neko when a task finishes | Not started | Neko makes the bot in BotFather; token goes in Hermes config only | Neko: bot token, never in chat | Neko | Oct 17 2:25 AM ET
H9 | Reach | GitHub login for Hermes on the new laptop (so it can read and push to repos) | Not started | Neko signs in once | Neko: login | Neko | Oct 17 2:25 AM ET
H10 | Gate | Test 1: Hermes reads this tracker and says what is open, with no errors | Not started | Run after H2 | H2 | Hermes | Oct 17 2:25 AM ET
H11 | Gate | Test 2: one small real task end to end (create a text file in a repo and push it) | Not started | Run after H9 and H10 | H9, H10 | Hermes | Oct 17 2:25 AM ET
H12 | Gate | Test 3: a scheduled task runs on its own (daily backup of Hermes memory and skills to a private repo) | Not started | Run after H11 | H11 | Hermes | Oct 17 2:25 AM ET
H13 | Pipeline | Hermes runs Derrick (Morning Word) end to end | On hold | Starts only after Tests 1-3 pass | H10, H11, H12 | Hermes | Oct 17 2:25 AM ET
H14 | Pipeline | White-hat pass on the finished pipeline: try to break it, list every weakness, fix them | On hold | After H13 is built | H13 | Claude | Oct 17 2:25 AM ET
H15 | Integration | Move Tracker A (Blessed Prayers and the rest) rows into this tracker | On hold | Only after Hermes is flawless. Neko says when | Neko: go-ahead | Claude | Oct 17 2:25 AM ET
H16 | Setup | Link the Claude desktop app on the new laptop to the Claude chat so Claude can see it | Not started | Mon 9 AM: open the chat on the new laptop, choose Link to this computer | Neko at the new laptop | Neko | Oct 17 2:25 AM ET

## Standing rules
Rule | Detail
Own tracker | This file is Hermes' tracker (Tracker B). The Blessed Prayers tracker (overnight/Claude-Work-Tracker.xlsx, Tracker A) stays separate. Neko, Oct 17, 2026: get Hermes running flawless first, then bring Tracker A's items in. No other sheets, docs or trackers for Hermes.
Gate | No Derrick or pipeline work until Tests 1, 2 and 3 (H10-H12) pass. Every claim of 'it works' needs the test output.
Money | Ask Neko before spending any of his money or credits. Free first. Any model spend needs his yes.
Secrets | Passwords, API keys and tokens never go in chat. They live only in Hermes config or repo secrets.
Safety | Dedicated machine: no personal logins in browsers Hermes can reach; Hermes commands run in the Docker sandbox once H6 is done.
Inherited | Nothing posts anywhere without Neko's yes on that exact file. KJV only for scripture. No 'tomorrow' promises in Derrick content. Never tag people in posts.
Update habit | After every piece of work: update Status, Next step and Updated on this sheet, run python3 tools/tracker_sync.py hermes/Hermes-Tracker.xlsx hermes/TRACKER.md, commit and push before replying. Updated holds date AND time in Eastern, like 'Oct 17 2:30 AM ET'; set Last updated on the Where we are tab to the same stamp.
Stale check | Before changing a row, read its Updated stamp. If newer than what you last read, git pull and reconcile first. Never overwrite a newer row with older information.
Integration | When Neko says Hermes is flawless, copy Tracker A rows here (same columns), mark them moved in Tracker A, and note it under How it was done.

## How it was done
Job | Method that worked | Where / notes
Set the Hermes model | Edit ~/.hermes/config.yaml: model: provider and default. Store keys with hermes config set <KEY_NAME> <value> (Neko types the key himself). Check with hermes doctor, start with hermes, switch provider with hermes model. | Reference from the pinggy.io Hermes guide. NOT yet run on this laptop.
Free model route (fallback) | OpenRouter free models: 20 requests/min, 50/day with no credits, 1,000/day after a one-time $10 credit purchase. Model must support tool calling and 64K+ context. Free model IDs change, so list fresh before choosing. | Research Oct 16-17. NVIDIA NIM gives free credits (about 40 req/min) as another fallback.
Sandbox | Hermes can run shell commands on the machine. Use the Docker terminal backend for any model not yet trusted. | Needs Docker Desktop with WSL2 (supported on Windows 10 22H2).