## Where we are
Where we are
Last updated | Oct 16 11:50 PM ET
Status | Count
Done
In progress
Blocked
On hold
Not started
Total
% done
Next up (Blocked and Not started, top of list)
Open the Tasks tab and filter Status. Blocked items name exactly what is missing.

## Tasks
ID | Project | Task | Status | Next step | Blocked by / waiting on | Owner | Updated
S1 | Sleep Bible | Psalms video live on Blessed Prayers YouTube + shop links in description | Done | None |  | Claude | Oct 16
S2 | Sleep Bible | John video rendered, mastered, checked | Done | None |  | Claude | Oct 16
S3 | Sleep Bible | Proverbs video rendered, mastered, checked | Done | None |  | Claude | Oct 16
S4 | Sleep Bible | John and Proverbs thumbnails (modest woman on beach, approved) | Done | None |  | Claude | Oct 16
S5 | Sleep Bible | Shop and book links in John, Proverbs, Psalms descriptions | Done | None |  | Claude | Oct 16
S6 | Sleep Bible | Upload John and Proverbs to YouTube as private with thumbnails | Blocked | Run youtube-upload workflow (privacy=private, thumbnail_path set) | YT_CLIENT_ID, YT_CLIENT_SECRET, YT_REFRESH_TOKEN missing from repo secrets | Neko | Oct 16
S7 | Sleep Bible | Derrick promos for John and Proverbs | Not started | Build after HeyGen voice fix | Derrick voice change in HeyGen; Neko go on promo credits | Claude | Oct 16
S8 | Sleep Bible | Genesis sleep reading | Not started | Needs Neko's go; no render exists | Neko go | Claude | Oct 16
S9 | Sleep Bible | Pinned comment with shop link on each sleep video | Not started | Add once videos are public |  | Claude | Oct 16
S10 | Sleep Bible | YouTube cards / end screens pointing to books | Not started | Set in Studio video editor |  | Claude | Oct 16
M1 | Morning Word | Day 4 (1 Peter 5:7) delivered by Buffer to YouTube, Instagram, TikTok | Done | None |  | Claude | Oct 16
M2 | Morning Word | Joshua 1:9 image card queued for 9 AM ET | Done | Confirm it sent |  | Claude | Oct 16
M3 | Morning Word | Derrick voice changed in HeyGen to the ElevenLabs Derrick Hughes clone | In progress | Neko is changing it | Neko changing voice in HeyGen | Neko | Oct 16
M4 | Morning Word | Derrick Day 5 and Day 6 videos built and scheduled | Not started | Build after M3. Nothing in Buffer for Oct 16-17 | M3 | Claude | Oct 16
P1 | Pinterest | Pin Etsy listings (14 pins live) | Done | Pin remaining listings (audiobooks, teen playbook, apparel) |  | Claude | Oct 16
P2 | Pinterest | Move 2 pins to the right board (I Wanna Die Different, Built to Carry) | Not started | Re-pin to Christian Books & Audiobooks |  | Claude | Oct 16
F1 | Outreach | Facebook posts on Blessed Prayers and Prince Nico pages | Not started | Post where group rules allow Etsy links | Facebook site permission in browser | Claude | Oct 16
G1 | Gossip teaching | 7-day scripts written, saved in repo | Done | None |  | Claude | Oct 16
G2 | Gossip teaching | Rewrite to Neko's corrections | On hold | Wait for his review | Neko must see scripts first | Neko | Oct 16
H1 | Shopify | First-pass niche research (night-shift sleep products) | Done | None |  | Claude | Oct 16
H2 | Shopify | Vet real CJ product pages for the 3 candidates | Not started | Open CJ pages and check reviews, shipping |  | Claude | Oct 16
A1 | Free avatar | Free-face test (InfiniteTalk or MuseTalk on Kaggle) | Not started | Neko says token is in; run test |  | Claude | Oct 16
S11 | Sleep Bible | Genesis sleep reading: render started 8:50 AM Oct 16 (sleep-render, tag sleep-genesis-chapters) | In progress | Run sleep-master (needs title frame), sleep-qa, sleep-glitch, write youtube.json | Upload blocked on YT secrets | Claude | Oct 16
M5 | Morning Word | Day 4 (1 Peter 5:7) built, Buffer-delivered Oct 16 5 AM; Neko said 'good, not the best' | Done | Rebuild only if Neko asks |  | Claude | Oct 16
M6 | Morning Word | Week 2 Days 2-7 and Oct 17+ not built | Blocked | Build after HeyGen voice change | Neko: HeyGen voice change | Neko | Oct 16
M7 | Morning Word | Free pipeline: Chatterbox voice + LiveTalk face on Kaggle (voice and face tests passed Oct 15) | In progress | 60-sec real-narration test; brightness drift fix; Kaggle->GitHub handoff test | Kaggle GITHUB_TOKEN secret (Neko says in); ElevenLabs credits at zero; intro/outro music missing | Claude | Oct 16
M8 | Morning Word | Alternative-workflow thread turns 77-184 unread (hit read limit) | Not started | Re-read after limit resets, update M7 | Hourly chat-read limit | Claude | Oct 16
M9 | Morning Word | Derek only thread turns 117-361 unread | Not started | Re-read after limit resets, reconcile Week 2 status | Hourly chat-read limit | Claude | Oct 16
E1 | Etsy | Etsy connector trial ends Oct 17; 4 empty drafts; journals/planners still in Desk Calendars | Not started | Neko decides on trial; Claude tidies drafts and categories | Neko: trial decision | Neko | Oct 16
E2 | Etsy | Facebook groups: Key live in Christian Fiction Fans; 4 posts in admin review; Married Twice unverified; Say Something About My Father blocked by safety check | In progress | Verify which posts went live; no new posting until Facebook allowed | Facebook site permission | Claude | Oct 16
E3 | Etsy | Six books still lack PDFs; Christian Anxiety Workbook has no PDF/description/tags | Not started | Neko supplies PDFs | Neko: PDFs | Neko | Oct 16
B1 | Books | Mother-in-law book 'The Empty Chair': ch 1-5 delivered, 6-13 to write | In progress | Neko reads/corrects ch 2-5, says 'next' for ch 6 | Neko review; Norman's father detail; check overlap with Mama's Boys | Neko | Oct 16
B2 | Books | Horrorcore verse flipped to testimony, Suno kit delivered | Done | Neko runs kit in Suno, reports; BPM 92 if too jazzy | Neko in Suno | Neko | Oct 16
T1 | Tech | Self-host laptop: new laptop (i5-7300U, 16GB) chosen; Docker not installed; Hermes free-model setup not started | Blocked | Set up Hermes after $10 OpenRouter decision | Neko: OpenRouter free vs $10; be at laptop | Neko | Oct 16
T2 | Tech | Replace trial connectors with free tools (Orshot, Buffer, TinyFish, Descript, ElevenLabs); Neko said 'different route' Oct 15 | On hold | Ask Neko the new route | Neko | Neko | Oct 16
R1 | Resume service | Aviation resume service: Wix page live ($49), card made, nothing posted, no sales; Neko doubts niche | On hold | Neko decides: pivot or drop | Neko: payment handles, logins, direction | Neko | Oct 16
X1 | Spending | Promo credits for John/Proverbs (~210 Flow credits each) - ask first; free path instead | On hold | Use free path or get yes | Neko: credit approval | Neko | Oct 16
X2 | Music | Psalms 82-150 glitch fix: closed by Neko ('leave it') | Done | None |  | Neko | Oct 16
D1 | Morning Word | LOCKED Oct 16: Derrick episodes Monday to Friday only; no Sat/Sun episodes | Done | Build Mon-Fri only |  | Neko | Oct 16
D2 | Morning Word | Main route is Google Flow; HeyGen only until its credits run out (renews Nov 15, will NOT be renewed) | Done | Use HeyGen credits on Derrick episodes before then |  | Neko | Oct 16
D3 | Morning Word | Mic-over-mouth Derrick still made in Flow (Sep 24 project, first tile in All media); Neko says it looks good. Use only for free-pipeline tests when lip-sync fails | Done | Animate only on Neko's go; check credit cost first |  | Claude | Oct 16
D4 | Morning Word | FALLBACK if Flow credits run out or Flow breaks: MiniMax H3 official API ($0.08/sec, about $1.20 per 15s). Self-hosting the open weights is NOT allowed in the U.S. (license excludes US). APIYI reseller $0.03/sec unverified for US use | On hold | Revisit only if Flow fails; one test clip first | Neko: sign up + key as repo secret | Neko | Oct 16
D5 | Morning Word | Flow credits (Pro): 1000/mo + 50 free/day. Lite 10, Fast 20, Quality 100 per clip. Keep clips 6-7s, lines under 20 words, use edits not full regenerates | Done | Run Lite test before finals |  | Claude | Oct 16
D6 | Morning Word | Monday Oct 19 Derrick episode: nothing built or queued in Buffer | Not started | Build after HeyGen voice change or in Flow | M3 (HeyGen voice) if using HeyGen | Claude | Oct 16
Z1 | Neko Zion | Joined 6 gospel reggae FB groups (instant, no approval) | Done | Join Roots Reggae Gospel, Jamaica Reggae Gospel Amen, Gospel/Christian Rap, Gospel Music History, Gospel Music Videos Network |  | Claude | Oct 16 11:50 PM ET
Z2 | Neko Zion | Word For Today pre-save posted in Gospel reggae (10.8K) and Reggae gospel songs (15.3K) | Done | None |  | Claude | Oct 16 11:50 PM ET
Z3 | Neko Zion | Push to Hymn Reimagined, Reggae Gospel, Reggae Gospel Link, GospelReggae.com, Zion Reggae Gospel: scheduled task Oct 18-20 10:47 AM ET, 3 groups per run, One Love One World video + pre-save | In progress | Task runs on its own; confirm posts after Oct 20 | Computer must be on with Claude desktop app open | Claude | Oct 16 11:50 PM ET
Z4 | Neko Zion | Word For Today promo video | Not started | Make after the pre-save push |  | Claude | Oct 16 11:50 PM ET
Z5 | Neko Zion | Copyright day Tue Oct 20, 2-5 PM ET on calendar | Done | None |  | Claude | Oct 16 11:50 PM ET
Z6 | Neko Zion | Fiverr license letters from Vaizal (8 PDFs): 1 of 8 read | In progress | Read other 7, map each to a song |  | Claude | Oct 16 11:50 PM ET
Z7 | Neko Zion | Locate song audio files and lyrics (not in Gmail label 'music and royalty stuff') | Not started | Search Drive and Gmail |  | Claude | Oct 16 11:50 PM ET
Z8 | Neko Zion | Copyright Office: Island of Peace first, then Word For Today and rest of One Love One World (that album filed 4/22/2026). AI origin disclosed briefly and excluded from claim | Not started | Tue Oct 20: Neko logs in, pays, uploads audio; Claude fills fields | Neko: login, payment, audio upload | Neko | Oct 16 11:50 PM ET
Z9 | Neko Zion | BMI, MLC, SoundExchange, Songtrust for other tracks | Not started | After copyright day |  | Claude | Oct 16 11:50 PM ET
Z10 | Neko Zion | Facebook Pages Prince Neko and Neko Zion not in Business Suite; X not connected | Not started | Fix Business Suite; connect X | Neko: page access | Neko | Oct 16 11:50 PM ET

## Standing rules
Rule | Detail
Promo links | Every sleep-Bible video and every promo for any book or channel carries the Kingdom Impact Shop link plus 3-4 relevant book links in the description. Set by Neko Oct 16, 2026.
Scripture | KJV only. Do not announce it.
Derrick | No 'tomorrow' promises. Never tag people in posts. Nothing posts without Neko's yes on that exact file.
Money | Ask before spending any of his money or credits. Prefer free options (Gemini Pro plan).
Asleep work | When Neko sleeps: work through the last threads, do the work, put it in overnight/ in the repo. No look-at-this asks.
Secrets | Passwords and tokens never in chat.
Update habit | After every piece of work, update Status, Next step and Updated on this sheet, commit and push before replying. Updated holds date AND time in Eastern, like 'Oct 16 11:50 PM ET'. Also set Last updated on the Where we are tab to the same stamp.
One tracker | This file is the only tracker. Read Tasks, Standing rules and How it was done before answering any where-are-we question or asking Neko for anything. Never create another sheet or tracker. Neko rule Oct 16, 2026.
Stale check | Before changing a row, read its Updated stamp. If it is newer than what you last read (another thread worked on it), git pull and reconcile first. Never overwrite a newer row with older information. Always git pull before editing and again before pushing.

## How it was done
Job | Method that worked | Where / notes
Derrick episode in Flow | Open Derrick project in Chrome (signed in as neko.husser@gmail.com). Add derrick-gray still as reference, type script clip (about 15 words), generate Veo 3.1 Lite 9:16. Stitch, caption, -14 LUFS in ffmpeg. Send ONE captioned MP4 for approval. | Project flow.google.com/u/0/project/0a90fb26-707c-45ae-aae4-61a8d163a56b. Keep other Chrome tabs closed. Screenshots in Chrome often time out; use get_page_text.
Make a new Derrick still in Flow | Flow side panel: ingredients (+) button, pick derrick-gray.png from the asset list, Add to prompt, type description, send. Agent confirms before generating; image is free (Nano Banana). | Done Oct 16 for the mic still.
Animate a still | Flow shows an Animate button under each still. Check the credit cost shown first; Lite is 10 credits. | Not tested yet.
Verse short or sleep video to Buffer | Render on GitHub Actions, commit mp4 to repo, queue in Buffer (YouTube, TikTok, Instagram) with raw.githubusercontent URL. | Buffer cap 10 queued per channel. See workflow-playbook memory.
Facebook group post or join | Built-in browser pane (needs laptop awake, pane visible), logged in as Blessed Prayers. Link posts only. | About 3 groups a day, read rules first.
Flow credit saving | Lite not Quality; one output; 6-7s clips; targeted edits instead of full regenerate; use the free daily 50 credits. | Source: Google Flow credits help page.
HeyGen voice fix | Voice picker, Import from ElevenLabs (Neko types his own API key) or Clone from approved sample. Voice must be ElevenLabs Derrick Hughes, deeper and more masculine. | Neko does the login/key step.
Copyright Office (eCO) | eco.copyright.gov in the built-in browser. Neko does login, payment and audio upload; Claude fills every other field. Suno-made audio is disclosed as AI and excluded from the claim; claim is lyrics and human production (Vaizal transfer of rights). | Fiverr license letters: fiverr.com/inbox/pesanmusik, open PDF link in the pane and read by screenshot.